## Sheet1
ID | USER STORY | OWNER | PRIORITY | EFFORT in story point (Guide: (Lowest) 1, 2, 4, 8 (Highest)) | Status | Definition of Done | Notes
1 | As an Administrator I want to have a public profile page so that customers can view my company information | Mohammed Ali | Critical | 1 | Completed | Admin profile view visible to other users, acceptance criteria met, unit tests passed, code reviewed by team and approved by product owner
2 | As an Administrator, I want to login so that I can manage my business and workers. | Mohammed Ali | Critical | 8 | Completed | Login view for admin completed, acceptance criteria met, unit tests passed, code reviewed by team and approved by product owner
3 | As a customer I want to visit the homepage with signup so that I can create My own profile | Mohammed Ali | Critical | 8 | Completed | Homepage view completed with sign up for in the homepage, acceptance criteria met, unit tests passed, code reviewed by team and approved by product owner
4 | As a customer, I want read about the AGME’s site in the ‘About Us’ Page, so that I can quickly identify where to read to understand more about this platform | Mohammed Ali | Critical | 1 | Completed | About Us page completed with title and description, accessible from menu, acceptance criteria met, unit tests passed, code reviewed by team and approved by product owner
5 | As a customer, I want to find contact information of AGME, so that I will be able to inquire of any questions and receive assistance | Mohammed Ali | Critical | 2 | Completed | Contact Us page completed with title and contact details, accessible from menu, acceptance criteria met, unit tests passed, code reviewed by team and approved by product owner
6 | As a customer, I want to access my account details so that I can check if they are accurate | Mohammed Ali | Critical | 2 | Completed | Customer profile page completed with title, personal contact details, bookings, accessible from menu, acceptance criteria met, unit tests passed, code reviewed by team and approved by product owner
7 | As a customer, I want to edit my profile details so that I can keep my information up-to-date for when I need to make bookings | Mohammed Ali | medium | 4 | Started | Customer profile page completed with title, personal contact details, bookings, editable, updatable and accessible from menu, acceptance criteria met, unit tests passed, code reviewed by team and approved by product owner
8 | As a customer, I want to login with my account, so that I can make bookings with my details | Mohammed Ali | Critical | 8 | Completed | Customer login view completed, accessible from menu, acceptance criteria met, unit tests passed, code reviewed by team and approved by product owner
9 | As a customer, I want to sign up, so that my details can be saved and I do not need to re-enters my details each time I make a new booking | Mohammed Ali | Critical | 2 | Completed | Customer register view completed, accessible from menu, acceptance criteria met, unit tests passed, code reviewed by team and approved by product owner
10 | As an administrator I want to add an employee so that the employee can access the system | Mohammed Ali | Critical | 2 | Not Started | Administrator accessible employee register view completed, accessible from menu, acceptance criteria met, unit tests passed, code reviewed by team and approved by product owner
11 | As an administrator I want to edit an employee’s detail so that their details can be up-to-date | Mohammed Ali | medium | 4 | Not Started | Administrator accessible employee profile view completed with personal contact details, service provided, scheduled hours, editable, updatable and accessible from menu, acceptance criteria met, unit tests passed, code reviewed by team and approved by product owner
12 | As an administrator I want to assign working hours to an employee so that the employee can be given their shift time | Mohammed Ali | Critical | 2 | Started | Administrator accessible employee profile view completed with scheduled hours and accessible from menu, acceptance criteria met, unit tests passed, code reviewed by team and approved by product owner
13 | As an administrator I want to edit the working hours of the employees so that their shift can be corrected or changed | Mohammed Ali | medium | 4 | Not Started | Administrators accessible employee profile view completed with scheduled hours, editable, updatable and accessible from menu, acceptance criteria met, unit tests passed, code reviewed by team and approved by product owner
14 | As an administrator I want to view all bookings so that I can showcase bookings | Mohammed Ali | high | 2 | Completed | Administrator profile view completed with scheduled bookings and accessible from menu, acceptance criteria met, unit tests passed, code reviewed by team and approved by product owner
15 | As an administrator I want to view worker availability so that I can allocate work | Mohammed Ali | high | 2 | Started | Administrator profile view completed with employee availability and accessible from menu, acceptance criteria met, unit tests passed, code reviewed by team and approved by product owner
16 | As a customer, I want to make bookings so that I can add it to my list of booked service | Mohammed Ali | high | 2 | Started | Booking view completed with employee services, availability, bookable to customer profile page and accessible from menu, acceptance criteria met, unit tests passed, code reviewed by team and approved by product owner
17 | As a customer, I want to view all the bookings that I have made so that I can ensure I made the correct bookings and keep track of the services I have booked | Mohammed Ali | high | 1 | Completed | Review booking history view completed is accessible through the menu when customer is signed in. acceptance criteria met, unit tests passed, code reviewed by team and approved by product owner.
18 | As a customer, I want to be able to search by date and time so that I can find available bookings based on my own schedule | Mohammed Ali | low | 2 | Not Started | Customer search view by date and time completed is accessible through the booking page when customer is signd in. Acceptance criteria met and code reviewed by team. approved by product owner
19 | As a customer, I want to be able to search by worker so that I can get the person I want and make a booking based on this worker’s availability | Mohammed Ali | low | 4 | Not Started | Customer search view by worker, completed is accessible through the booking page when customer is signd in. Acceptance criteria met and code reviewed by team. approved by product owner
20 | As a customer, I want to be able to search service so that I can get a list of who can provides the service I want | Mohammed Ali | low | 2 | Not Started | Customer search view by service completed is accessible through the booking page when customer is signd in. Acceptance criteria met and code reviewed by team. approved by product owner
21 | As a customer, I want to be able to view the service by the date/time, so that I can ensure I will only make bookings when I am available | Mohammed Ali | high | 1 | Not Started | Customer can view service time completed is accessible through the booking page when customer is signd in. Acceptance criteria met and code reviewed by team. approved by product owner
22 | As a customer, I want to view the employee who provides the service, so that I can ensure the worker who will provide the service is the person that I want. | Mohammed Ali | high | 2 | Not Started | Customer can view service provider completed is accessible through the booking page when customer is signd in. Acceptance criteria met and code reviewed by team. approved by product owner
23 | As a customer, I want to view what service I am booking, so that I know I am booking the service I want. | Mohammed Ali | high | 1 | Not Started | Customer can view service offered completed is accessible through the booking page when customer is signd in. Acceptance criteria met and code reviewed by team. approved by product owner
24 | As a customer I want to edit my name so I can update my name | Mohammed Ali | low | 2 | Not Started | Customer can edit own name accessible through customer profile when customer is signed in. Acceptance test and unit tests met, code reviewed by team and approved by product owner
25 | As a customer I want to edit my username so I can update my username | Mohammed Ali | low | 2 | Not Started | Customer can edit own Username accessible through customer profile when customer is signed in. Acceptance test and unit tests met, code reviewed by team and approved by product owner
26 | As a customer I want to edit my password so I can login with a new password | Mohammed Ali | high | 2 | Not Started | Customer can edit own password accessible through customer profile when customer is signed in. Acceptance test and unit tests met, code reviewed by team and approved by product owner
27 | As a customer I want to edit my address so that my address is updated. | Mohammed Ali | low | 2 | Not Started | Customer can edit own address accessible through customer profile when customer is signed in. Acceptance test and unit tests met, code reviewed by team and approved by product owner
28 | As a customer I want to edit my contact number so that I can update my contact number. | Mohammed Ali | medium | 2 | Started | Customer can edit own contact number accessible through customer profile when customer is signed in. Acceptance test and unit tests met, code reviewed by team and approved by product owner
29 | As a customer, I want to be able to cancel any of my future bookings from the system, up until 48 hours before the booking start date/time. | Mohammed Ali | medium | 4 | Completed | Customer can cancel existing booking accessible through bookings page when customer is signed in. Acceptance test and unit tests met, code reviewed by team and approved by product owner
30 | As a customer I want to view a history of bookings so I can see all the bookings I’ve made | Mohammed Ali | medium | 1 | Not Started | Customer can view existing booking accessible through bookings page when customer is signed in. Acceptance test and unit tests met, code reviewed by team and approved by product owner
31 | As a employee I want to view a history of all bookings so I can see all my confirmed bookings | Mohammed Ali | medium | 2 | Not Started | Employee can view all existing booking accessible through bookings page when employee is signed in. Acceptance test and unit tests met, code reviewed by team and approved by product owner
32 | As a Administrator I want to view a history of all bookings so I can see all confirmed bookings | Mohammed Ali | critical | 4 | Not Started | administrator can view all existing booking accessible through bookings page when administrator is signed in. Acceptance test and unit tests met, code reviewed by team and approved by product owner
33 | As an employee, I want to have a profile to see my details. | Mohammed Ali | high | 2 | Started | Employee can view own profile when signed in as employee. acceptance tests and unit test criteria met, code reviewed by team and approved by product owner
34 | As an employee, I want to see what services I will be providing. | Mohammed Ali | high | 2 | Not Started | Employee can view own services offered when signed in as employee. acceptance tests and unit test criteria met, code reviewed by team and approved by product owner
35 | As an employee, I want to see what assigned working hours I have been given so that I can know my working hours. | Mohammed Ali | high | 2 | Not Started | Employee can view own roster when signed in as employee. acceptance tests and unit test criteria met, code reviewed by team and approved by product owner
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52