## Sprint 1
SPRINT #1 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | DoD
3 | As a administrator, I want to visit the | 3.1 | Create Database | M |  |  | x | Data base with functionality created
| homepage with signup so that I can | 3.2 | Create Backend | M |  |  | x | Create backend to link database to frontend
| create My own profile | 3.3 | Test Backend with postmap | J |  | x |  | Junit testing
|  | 3.4 | Create Homepage | B |  |  | x | Homepage present after entering address
|  | 3.5 | Create front end sign up | B |  |  | x | Homepage with sign up button and sign up page
|  | 3.6 | User acceptance test | B |  | x |  | user acceptance tests met criteria
9 | As a customer, I want to sign up, so | 9.1 | Create Database | M |  |  | x | Data base with functionality created
| that my details can be saved and I do | 9.2 | Create Backend | M |  |  | x | Create backend to link database to frontend
| not need to re-enters my details | 9.3 | Test Backend with postmap | J |  | x |  | Junit testing
| each time I make a new booking | 9.4 | Create Login page | S |  |  | x | Create login page
|  | 9.5 | Create front end login | S |  |  | x | Create login function
|  | 9.6 | Create customers | M |  |  | x | insert customers into database
4 | As a customer, I want read about the | 4.1 | Create About us page | B |  |  | x | Create about us page
| AGME’s site in the ‘About Us’ Page, | 4.2 | Acceptance tests | B |  |  | x | create about us page mets test criteria
so that I can quickly identify where
to read to understand more about
this platform
5 | As a customer, I want to find | 5.1 | Create contact us page | B |  |  | x | create contact us page
| contact information of AGME, so that | 5.2 | Acceptance tests | B |  |  | x | contact us page meets test criteria
I will be able to inquire of any
questions and receive assistance

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #NAME?
| Previous Year | #REF! | #NAME?
| Position | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | As a administrator, I want to visit the | #N/A | #N/A | #N/A | #N/A | #N/A
2 | homepage with signup so that I can | #N/A | #N/A | #N/A | #N/A | #N/A
3 | create My own profile | #N/A | #N/A | #N/A | #N/A | #N/A
4 | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR!
5 | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | As a customer, I want to sign up, so | #N/A | #N/A | #N/A | #N/A | #N/A
8 | that my details can be saved and I do | #N/A | #N/A | #N/A | #N/A | #N/A
9 | not need to re-enters my details | #N/A | #N/A | #N/A | #N/A | #N/A
10 | each time I make a new booking | #N/A | #N/A | #N/A | #N/A | #N/A
11 |  | #N/A | #N/A | #N/A | #N/A | #N/A
12 |  | #N/A | #N/A | #N/A | #N/A | #N/A
13 | As a customer, I want read about the | #N/A | #N/A | #N/A | #N/A | #N/A
14 | AGME’s site in the ‘About Us’ Page, | #N/A | #N/A | #N/A | #N/A | #N/A
15 | so that I can quickly identify where | #N/A | #N/A | #N/A | #N/A | #N/A
16 | to read to understand more about | #N/A | #N/A | #N/A | #N/A | #N/A
17 | this platform | #N/A | #N/A | #N/A | #N/A | #N/A
18 | As a customer, I want to find | #N/A | #N/A | #N/A | #N/A | #N/A
19 | contact information of AGME, so that | #N/A | #N/A | #N/A | #N/A | #N/A
20 | I will be able to inquire of any | #N/A | #N/A | #N/A | #N/A | #N/A
21 | questions and receive assistance | #N/A | #N/A | #N/A | #N/A | #N/A
22 |  | #N/A | #N/A | #N/A | #N/A | #N/A
23 |  | #N/A | #N/A | #N/A | #N/A | #N/A
24 |  | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A