## Sprint 1
SPRINT #1 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | DoD
3 | As a administrator, I want to visit the | 3.1 | Create Database | M |  |  | x | Data base with functionality created
| homepage with signup so that I can | 3.2 | Create Backend | M |  |  | x | Create backend to link database to frontend
| create My own profile | 3.3 | Test Backend with postmap | J |  |  | x | Junit testing
|  | 3.4 | Create Homepage | B |  |  | x | Homepage present after entering address
|  | 3.5 | Create front end sign up | B |  |  | x | Homepage with sign up button and sign up page
|  | 3.6 | User acceptance test | B |  |  | x | user acceptance tests met criteria
9 | As a customer, I want to sign up, so | 9.1 | Create Database | M |  |  | x | Data base with functionality created
| that my details can be saved and I do | 9.2 | Create Backend | M |  |  | x | Create backend to link database to frontend
| not need to re-enters my details | 9.3 | Test Backend with postmap | J |  |  | x | Junit testing
| each time I make a new booking | 9.4 | Create Login page | S |  |  | x | Create login page
|  | 9.5 | Create front end login | S |  |  | x | Create login function
|  | 9.6 | Create customers | M |  |  | x | insert customers into database
4 | As a customer, I want read about the | 4.1 | Create About us page | B |  |  | x | Create about us page
| AGME’s site in the ‘About Us’ Page, | 4.2 | Acceptance tests | B |  |  | x | create about us page mets test criteria
so that I can quickly identify where
to read to understand more about
this platform
5 | As a customer, I want to find | 5.1 | Create contact us page | B |  |  | x | create contact us page
| contact information of AGME, so that | 5.2 | Acceptance tests | B |  |  | x | contact us page meets test criteria
I will be able to inquire of any
questions and receive assistance

## Sprint 2
SPRINT #2 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | DoD
1 | As an Administrator I want to have a public profile page so that customers can view my company information | 1.1 | Create Front end | B |  |  | x | Create a public profile page and frontend links to the backend databases
|  | 1.2 | Test acceptance tests | B |  |  | x | Create a public profile page and passes aceptance tests
B
2 | As an Administrator, I want to login | 2.1 | Create Frontend | M |  |  | x | Login Page with login functionality implemented
| so that I can manage my business and workers. | 2.2 | Create Backend | M |  |  | x | Login Backend functioning
|  | 2.3 | Create Administrator | M |  |  | x | An administrator user present in database
|  | 2.4 | Front end acceptance tests | M |  |  | x | Multiple acceptance tests applied and completed
|  | 2.5 | Test with unit tests | M |  |  | x | Unit tests applied and completed
14 | As an administrator I want to view all bookings so that I can showcase bookings | 14.1 | Create Booking frontend | JL |  |  | x | Create View of booking for frontend
|  | 14.2 | Create backend | JL |  |  |  | Create backend logic
|  | 14.3 | Acceptance test | S |  |  | x | Acceptance tests that meet criteria
|  | 14.4 | Test with unit tests | JL |  |  | x | Test with junit
17 | As a customer, I want to view all the bookings that I have made so that I can ensure I made the correct bookings and keep track of the services I have booked | 17.1 | Login as customer | SI |  |  | x | Create view of Login
|  | 17.2 | Set up existing bookings | JL |  |  | x | Wire backend to frontend
|  | 17.3 | Acceptance tests | Si |  |  | x | User booking page is complete and passes acceptance tests
29 | As a customer, I want to be able to cancel any of my future bookings from the system, up until 48 hours before the booking start date/time. | 29.1 | Create view of cancel button |  |  |  | x | Create cancel view for booking
|  | 29.2 | create backend cancel feature | JL |  |  | x | Create Cancel methods for backend
|  | 29.3 | unit tests | JL |  |  | x | Test with Junit and postman
8 | As a customer, I want to login with my account, | 8.1 | Create Frontend | M |  |  | x | Create view for customer login
| so that I can make bookings with my details. | 8.2 | Create Backend | M |  |  | x | Create backend logic
|  | 8.3 | Test backend with postman | M |  |  | x | Get jwt when successful login
|  | 8.4 | Test with unit tests | M |  |  | x | Covered most of login cases and have them pass
16 | As a customer, I want to make bookings so that I can add it to my list of booked service | 16.1 | Create Booking webpage | JL |  |  | x | Booking page is created with user's view
|  | 16.2 | Create booking backend | JL |  |  | x | Booking backend is established and functional
|  | 16.3 | Acceptance test | SI |  |  | x | Acceptance tests completed according to user stories
|  | 16.4 | Unit tests | JL |  | x |  | Unit tests created and applied
6 | As a customer, I want to access my account details so that I can check if they are accurate | 6.1 | Create Frontend | B |  |  | x | Create frontend view of Customer profile account
|  | 6.2 | Create Backend | B |  | x |  | Create backend logic for customer profile
|  |  | acceptance tests | B |  | x |  | Successful acceptance tests that meet criteria
|  |  | Unit tests | B | x |  |  | Junit tests with postman

## Sprint 3
SPRINT #3 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | DoD
7 | As a customer, I want to edit my profile | 7.1 | Create Edit profile view | S |  |  | x | Create Frontend that links to backend
| details so that I can keep my information | 7.2 | Create Edit profile backend | S |  |  | x | create backend logic to wire to Frontend
| up-to-date for when I need to make bookings. | 7.3 | Acceptance tests | S |  |  | x | Acceptance tests that meet criteria
|  | 7.4 | Unit tests | S |  |  | x | Junit tests
12 | As an administrator I want to | 12.1 | Create Roster logic | M |  |  | x | Create data logic for rosters
| assign working hours to an employee so | 12.2 | Wire view to backend | M |  |  | x | Link Backend and frontend for Work hours
| that the employee can be given their | 12.3 | Acceptance tests | M |  |  | x | Acceptance tests that meet criteria
| shift time. | 12.4 | Unit tests | M |  |  | x | Junit tests
13 | As an administrator I want to edit the working | 13.1 | Wire view to backend | JV |  |  | x | Link Backend and frontend for Work hours
| hours of the employees so that their shift can | 13.2 | Acceptance tests | JV |  |  | x | Acceptance tests that meet criteria
| be corrected or changed | 13.3 | Unit tests | JV |  |  | x | Junit tests
15 | As an administrator I want to view | 15.1 | Create Front end view | JL |  |  | x | Create Frontend view for admins to see availability
| worker availability so that I can | 15.2 | Wire frontend to backend logic | JL |  |  | x | Create backend logic
| allocate work. | 15.3 | Acceptance tests | JL |  |  | x | Acceptance tests that meet criteria
|  | 15.4 | Unit tests | JL |  |  | x | Junit tests to satisfy criteria
16 | As a customer, I want to make bookings | 16.1 | Create Front end view | JL |  |  | x | Create Frontend view for customers
| so that I can add it to my list of booked | 16.2 | Wire frontend to backend logic | JL |  |  | x | Create backend logic
| service | 16.3 | Acceptance tests | JL |  |  | x | Acceptance tests that meet criteria
|  | 16.4 | Unit tests | JL |  |  | x | Junit tests to satisfy criteria
28 | As a customer I want to edit my contact | 28.1 | Create Frontend view | B |  |  | x | Create profile page edit view
| number so that I can update my contact | 28.2 | Create backend logic | B |  |  | x | create backend logic for edit profile
| number. | 28.3 | Acceptance tests | B |  |  | x | Acceptance tests that meet criteria
|  | 28.4 | Unit tests | B |  |  | x | Junit tests
32 | As an employee, I want to have a profile | 33.1 | Create Frontend view | B |  |  | x | Create employee profile page
| to see my details. | 33.2 | Acceptance tests | B |  |  | x | Create logic for employee profile page
|  | 33.3 | Unit tests | B |  |  | x | Acceptance tests that meet criteria
[7 empty] | x | Unit tests satisfy criteria
33 | As an employee, I want to have a profile | 33.1 | Create Frontend view | B |  |  | x | Create employee profile page
| to see my details. | 33.2 | Create Backend Logic | B |  |  | x | Create logic for employee profile page
|  | 33.3 | Acceptance tests | B |  |  | x | Acceptance tests that meet criteria
|  | 33.4 | Unit tests | B |  |  | x | Unit tests satisfy criteria

## Sprint 4
SPRINT #4 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | DoD
10 | As an administrator I want to add an | 10.1 | Create adding function | M |  |  | x | Create backend employee add function
| employee so that the employee can | 10.2 | Create Front end view | M |  |  | x | Create Front end view of Add employee
| access the system. | 10.3 | unit testing | M |  |  | x | Create unit tests
|  | 10.4 | Acceptance testing | M |  |  | x | Create Acceptance tests
11 | As an administrator I want to edit an | 11.1 | Create Edit backend | M |  |  | x | Create backend employee edit function
| employee’s detail so that their details | 11.2 | Create Front end view | M |  |  | x | Create Front end view of Add employee
| can be up-to-date | 11.3 | unit testing | M |  |  | x | Create unit tests
|  | 11.4 | Acceptance testing | M |  |  | x | Create Acceptance tests
21 | As a customer, I want to be able | 21.1 | Create Front end view | S |  |  | x | Create Front end view of employee roster
| to view the date/time of the service | 21.2 | unit testing | S |  |  | x | Create unit tests
| , so that I can ensure I will only make | 21.3 | Acceptance testing | JL |  |  | x | Create Acceptance tests
bookings when I am available
22 | As a customer, I want to view who | 22.1 | Create Front end view | S |  |  | x | Create Front end view of employee services
| provides the service, so that I can ensure | 22.2 | unit testing | S |  |  | x | Create unit tests
| the employee who provides the service | 22.3 | Acceptance testing | JL |  |  | x | Create Acceptance tests
is the person that I want.
23 | As a customer, I want to view what | 23.1 | Create Front end view | B |  |  | x | Create Front end view of services
| service I am booking, so that I know | 23.2 | unit testing | B |  |  | x | Create unit tests
| I am booking the service I want. | 23.3 | Acceptance testing | JL |  |  | x | Create Acceptance tests
24 | As a customer I want to edit my | 24.1 | Create Front end view | B |  |  | x | Create Front end view of edit name
| name so I can update my name | 24.2 | unit testing | B |  |  | x | Create unit tests
|  | 24.3 | Acceptance testing | JL |  |  | x | Create Acceptance tests
25 | As a customer I want to edit my | 25.1 | Create Front end view | B |  |  | x | Create Front end view of edit username
| username so I can update my username | 25.2 | unit testing | B |  |  | x | Create unit tests
|  | 25.3 | Acceptance testing | JL |  |  | x | Create Acceptance tests
26 | As a customer I want to edit my password | 26.1 | Create Front end view | B |  |  | x | Create Front end view of edit password
| so I can login with a new password | 26.1 | unit testing | B |  |  | x | Create unit tests
|  | 26.2 | Acceptance testing | JL |  |  | x | Create Acceptance tests
27 | As a customer I want to edit my | 27.1 | Create Front end view | B |  |  | x | Create Front end view of edit address
| address so that my address is updated. | 27.2 | unit testing | B |  |  | x | Create unit tests
|  | 27.3 | Acceptance testing | JL |  |  | x | Create Acceptance tests

## Sprint 5
SPRINT #5 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | DoD
18 | As a customer, I want to be able to search | 18.1 | Create Front end view |  |  |  | x | Create Front end view of Search booking by date and time
| by date and time so that I can find available | 18.2 | Acceptance testing |  |  |  | x | Create Acceptance tests
bookings based on my own schedule
19 | As a customer, I want to be able to search | 19.1 | Create Front end view |  |  |  | x | Create Front end view of Search booking by worker
| by worker so that I can get the person | 19.2 | Acceptance testing |  |  |  | x | Create Acceptance tests
I want and make a booking based on this
worker’s availability
20 | As a customer, I want to be able to search | 20.1 | Create Front end view |  |  |  | x | Create Front end view of Search booking by service
| service so that I can get a list of who | 20.2 | Acceptance testing |  |  |  | x | Create Acceptance tests
can provides the service I want
31 | As a employee I want to view a history | 31.1 | Create Front end view |  |  |  | x | Create Front end view of Booking history
| of all bookings so I can see all my | 31.2 | Wire to backend |  |  |  | x | Link frontend to back end
| confirmed bookings | 31.3 | Acceptance testing |  |  |  | x | Create Acceptance tests
34 | As an employee, I want to see what | 34.1 | Create Front end view |  |  |  | x | Create Front end view of Employee services
| services I will be providing. | 34.2 | Acceptance testing |  |  |  | x | Create Acceptance tests
35 | As an employee, I want to see what | 35.1 | Create Front end view |  |  |  | x | Create Front end view of Employee roster
| assigned working hours I have been | 35.2 | Acceptance testing |  |  |  | x | Create Acceptance tests
given so that I can know my working hours.

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #NAME?
| Previous Year | #REF! | #NAME?
| Position | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | As a administrator, I want to visit the | #N/A | #N/A | #N/A | #N/A | #N/A
2 | homepage with signup so that I can | #N/A | #N/A | #N/A | #N/A | #N/A
3 | create My own profile | #N/A | #N/A | #N/A | #N/A | #N/A
4 | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR!
5 | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | As a customer, I want to sign up, so | #N/A | #N/A | #N/A | #N/A | #N/A
8 | that my details can be saved and I do | #N/A | #N/A | #N/A | #N/A | #N/A
9 | not need to re-enters my details | #N/A | #N/A | #N/A | #N/A | #N/A
10 | each time I make a new booking | #N/A | #N/A | #N/A | #N/A | #N/A
11 |  | #N/A | #N/A | #N/A | #N/A | #N/A
12 |  | #N/A | #N/A | #N/A | #N/A | #N/A
13 | As a customer, I want read about the | #N/A | #N/A | #N/A | #N/A | #N/A
14 | AGME’s site in the ‘About Us’ Page, | #N/A | #N/A | #N/A | #N/A | #N/A
15 | so that I can quickly identify where | #N/A | #N/A | #N/A | #N/A | #N/A
16 | to read to understand more about | #N/A | #N/A | #N/A | #N/A | #N/A
17 | this platform | #N/A | #N/A | #N/A | #N/A | #N/A
18 | As a customer, I want to find | #N/A | #N/A | #N/A | #N/A | #N/A
19 | contact information of AGME, so that | #N/A | #N/A | #N/A | #N/A | #N/A
20 | I will be able to inquire of any | #N/A | #N/A | #N/A | #N/A | #N/A
21 | questions and receive assistance | #N/A | #N/A | #N/A | #N/A | #N/A
22 |  | #N/A | #N/A | #N/A | #N/A | #N/A
23 |  | #N/A | #N/A | #N/A | #N/A | #N/A
24 |  | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A